## Sheet1
Description: | Type: | Piority: | Status: | Date reported: | Date updated:
Update does not resize text | Bug | Medium | Fixed | 2020-08-08 | 2020-08-12
After selecting a unit, editing drop does not allow to go to blank or zero | Bug | Medium | Fixed | 2020-08-08 | 2020-08-13
Unit doesn't intersect move with dash line | Bug | low | Fixed | 2020-08-08 | 2020-08-08
dash line does not move to the right all the way when edited | Bug | Medium | Fixed | 2020-08-08 | 2020-08-08
Printing in chrome with dash lines have line through dash | Bug | low | Fixed | 2020-08-08 | 2020-08-15
After editing, text fields don't revert back to previous customer | Bug | Medium | Fixed | 2020-08-09 | 2020-08-09
Make trailer text change after selecting different truck | Bug | low | Fixed | 2020-08-09 | 2020-08-09
sideCanvas does not use updated add function. Fix did not upload | Bug | low | Fixed | 2020-08-09 | 2020-09-10
When typing new customer, change drop to "" unless customer is found | Bug | low | Fixed | 2020-08-09 | 2020-08-13
Customer text says undefined if customer is blank | Bug | low | Fixed | 2020-08-09 | 2020-09-10
Add editing mode that disables adding a unit | Feature | Medium | Done | 2020-08-09 | 2020-10-17
Unknown cause - after deleting an unit, it still says it exists when re-adding. Units.length appears to still be correct after deleting the unit. Problem seems to be linked with checkIfUnitIDExists. Temp fix reverted checkIfUnitIDExists to previous version. | Bug | High | Temp Fix | 2020-08-09 | 2020-08-09
Increase size of middle line | Feature | High | Done | 2020-08-09 | 2020-08-09
When updating unit, check if drop exists. If it does cancel the update. Only happens if customer name is different. | Bug | Medium | Fixed | 2020-08-13 | 2020-08-13
After updating unit, currentCust can perminately change. UPDATE: Doesn't seem to be affected anymore | Bug | Medium | Fixed | 2020-08-15 | 2020-09-10
Error dialog for update incorrectly displays which customer | Bug | Low | Fixed | 2020-08-15 | 2020-08-15
Make unit text smaller to fit in more | Feature | High | Done | 2020-08-18 | 2020-10-17
Make pocket doors double stackable. UPDATE: Not necessary | Feature | Medium | On HOLD | 2020-08-23
Hide sideBar scrollbar on webkit | Bug | Low | Fixed | 2020-08-23 | 2020-09-02
Unit list is undefined | Bug | High | Fixed | 2020-08-23 | 2020-08-23
Add dialog to remove unit, yes and no | Feature | High | Done | 2020-08-23 | 2020-09-20
If updating unit from width above 24 to below 24, text does not go sideways | Bug | Low | Fixed | 2020-09-05 | 2020-09-10
Add a way to easily change drops | Feature | Medium | Done | 2020-09-02 | 2020-09-10
Implement a solution for dropmenu's not showing all of content on small resolutions | Bug | Medium | Done | 2020-09-11 | 2020-09-20
Sort by drop then by width | Feature | Low |  | 2020-09-12
Restore from previous session | Feature | Low |  | 2020-09-12
Add keyboard sortcuts | Feature | Low |  | 2020-09-12
Drag units onto canvas without need to click twice | Feature | Low |  | 2020-09-12
Implement save feature | Feature | Medium | Done | 2020-09-12 | 2020-10-24
When selecting a different customer unit and then selecting off, rack toggle stays on the previous selected unit | Bug | High | Fixed | 2020-09-26 | 2020-09-26
When selecting a unit check rack does not update | Bug | Low | Fixed | 2020-09-26 | 2020-09-26
Drops can be the same if adding only to rack | Bug | Medium | Fixed | 2020-09-27 | 2020-09-30
List id doesn't include anything after a space | Bug | High | Fixed | 2020-09-27 | 2020-09-28
Update sometimes rotates text | Bug | Medium | Fixed | 2020-09-28 | 2020-09-30
Add edit button | Feature | Medium | Done | 2020-10-01 | 2020-10-16
Disable tag information on textbox when clicked. Instead should be on edit button | Bug | Medium | Fixed | 2020-10-17 | 2020-10-25
After moving units, sometimes the current customer is changed Update: happens when you click on more than one unit, it assigns current unit to the second last clicked unit | Bug | High | Fixed | 2020-10-17 | 2020-10-17
Add unit count for total lengths and total shorts | Feature | High | Done | 2020-10-17 | 2020-10-17
Remove horizontal and vertical scrolling of canvas being added after loading a save | Bug | Medium | Fixed | 2020-10-22 | 2020-10-22
Sometimes edit button has to be clicked twice | Bug | Low | Fixed | 2020-10-22 | 2020-10-25
CSS for lists causes width to be too big | Bug | Medium | Fixed | 2020-10-22 | 2020-11-01
height is too small after update | Bug | Medium | Fixed | 2020-10-24 | 2020-10-25
location should be set to blank after deselection | Bug | Medium | Fixed | 2020-10-24 | 2020-10-24
Tabbing to location field should skip height and width sliders | Bug | Medium | Fixed | 2020-10-24 | 2020-10-24
Disable preview when unit is selected | Bug | Medium |  | 2020-10-24
Implement past version link | Feature | Medium | Done | 2020-10-24 | 2020-10-25
Updating unit with no location to a location doesn't shorten customer name for location to be beside ae | Bug | Medium | Fixed | 2020-10-24 | 2020-10-25
Editing button can stop working | Bug | High | Fixed | 2020-10-24 | 2020-11-01
Preview is streched when location on bottom | Bug | Low | Fixed | 2020-10-24 | 2020-10-25
Add way to have multiple racks | Feature | Medium |  | 2020-10-25 | 2020-10-25
Coment should not use snap to grid | Bug | Medium | Fixed | 2020-10-25 | 2020-10-25
Tag should not be empty/Units with no TAG number | Bug | Medium | Fixed | 2020-10-26 | 2020-10-27
Unit list isn't draggable until second click. This is due to calling listUnits on click that generates a new drag handler | Bug | Medium | Fixed | 2020-10-28 | 2020-11-01
Implement Add/Remove to list | Feature | High | Done | 2020-10-26 | 2020-11-01
Selecting unit from list doesn't update customer fields | Bug | High | Fixed | 2020-11-01 | 2020-11-02
Handle unit.inCanvas is null for some units when dragging from list | Bug | High | Fixed | 2020-11-01 | 2020-11-02
When add button is pressed, current customer needs to be changed | Bug | Medium | Fixed | 2020-11-01 | 2020-11-02
Implement total units and customers not in canvas | Feature | High | Done | 2020-11-02 | 2020-11-02
OnChange removes selection of unitList if unit is not in canvas | Bug | Medium | Fixed | 2020-11-02 | 2020-11-03
Rare bug not allowing customer to be created | Bug | High | Fixed | 2020-11-03 | 2020-11-03
When adding only customer to rack, customer says it's not in truck until onChange on customer. | Bug | Medium | Fixed | 2020-11-03 | 2020-11-03
When drag and dropping a unit from unit list, if the unit preview causes the list to shift where the mouse is on a different index of the unit list it'll cause an error for sortable js | Bug | High | Fixed | 2020-11-07 | 2020-11-07
Unit edit button stops working when using straps | Bug | Medium | Fixed | 2020-11-07 | 2020-11-07
Loading sometimes doesn't restore trailer text | Bug | Medium | Fixed | 2020-11-07 | 2020-11-07
Update unit only adds to weight and not removes previous weight | Bug | High | Fixed | 2020-12-05 | 2020-12-05
Changelog div text appears on webpage sometimes | Bug | Low | Fixed | 2020-12-05 | 2020-12-05
Implement a barcode feature for turckID scanning | Feature | High |  | 2020-12-06
Tools sometimes unselectable and doesn't add to weight after changing truck | Bug | High |  | 2020-12-06
Update changes font size